## Slide 1: “Women Dialogue” Program (WD) Phase 2
Main findings and lessons learned

## Slide 2: What is WD Program about?
Since 2013, WD brings together 17 secularist and faith-driven local women's organizations:
To create a sustainable exchange Platform,
To build mutual trust and respect,
To discover shared interests beyond ideologically-driven differences and stereotypes
To make the case that there is always room for a common space for dialogue

## Slide 3: What is WD Phase 2 about?
Builds on the Phase 1 achievements in order to:
Deepen the dialogue among participants and their respective constituencies and expand its scope to new CSO
Provide intensive training on Mediation, Negotiation, Advocacy and Communication,
Engage the NGOs in joint legal advocacy

## Slide 4: What are the objectives of WD Phase 2?
Improve positive attitudes towards dialogue
Enhance group cohesion
Improve participants’ skills in Mediation, Negotiation and Advocacy

## Slide 5: WD Phase 2 Effectiveness
WD Phase 2:
Successfully addressed participants’ positive attitudes towards dialogue
Managed to work out moments of high tension
Created a suitable environment for sincere dialogue
Enhanced mutual exchanges and relationships that led to greater cohesion among participants
Improved participants’ skills in Mediation and Negotiation
Launched an advocacy campaign on a draft law on gender parity in public employment
Met participants’ expectations on Advocacy training BUT participants ARE NOT making use of these skills in the ongoing campaign

## Slide 6: WD Phase 2 key findings (I)
Great motivation to make the project succeed
  BUT participants perceive a “responsibility to succeed” as a leitmotiv throughout the “Women Dialogue” Program.
    This may lead participants to focus on seeking agreement “at all costs” rather than building agreement on a solid basis of mutual understanding.
Reliance on personal relationships as a guarantee to reach agreement
  “Knowing each other’s personal story” as an important factor
  BUT, progress on relationships has been mainly fueled by personal affinities while discovering common interests/values is still underdeveloped among participants
    As a result, misperceptions and prejudices still remain among participants

## Slide 7: WD Phase 2 key findings (II)
Avoid “sensitive” subjects as a strategy to “save” the dialogue
  The dialogue is “smooth” as long as topics like the CEDAW convention or the law on heritage are not discussed. Not surprisingly the CEDAW was once again, the “bone of contention”
  “Sensitive” subjects made some participants revert to their negative attitudes towards the dialogue: prejudices, interrupted discussions and sometimes personal offenses
Good (and improved) personal relationships
  BUT only within the Platform: once the WD Program comes to an end participants’ relations do not exceed some occasional exchanges
  BUT no institutional collaboration between the NGOs

## Slide 8: WD Phase 2 key findings (III)
Participants made use of some mediation practices learnt in the program that proved to be effective.
  a “committee of wise women” was set up after the discussions stopped over the CEDAW reference
  BUT the intervention of the trainer has been fundamental to overcome the stalemate
The “wait and see” attitude is a serious deterrent to mutual cooperation between NGOs
  This is not particularly due to a shortage of ideas BUT participants still look towards SFCG to take initiatives and engage them in common actions

## Slide 9: WD Phase 2 key findings (IV)
From the NGOs leaders’ perspective, continuous change in the group composition seems to be a factor that reduces the effectiveness of the program
Shared awareness by all civil society members and regardless of their ideological or religious backgrounds that in terms of women's rights, and despite the progress made, there is still a long way to go.
Time seems propitious for advocacy initiatives with Parliamentarians and policy-makers in general
  BUT public awareness-raising should not be neglected so that the law is not felt to be disconnected from ground realities

## Slide 10: Lessons learned (I)
Dialogue is not an objective per se but
  is all about a process that participants must make their own in order to avoid reverting to their former negative behavior/attitudes as it seems, to some extents to be the case in Phase 2.
  The NGOs participating in the Women Dialogue Phase 2 are not taking advantage of the political momentum which offers huge opportunities for civil society to make its case.
  Incentives (joint actions/ partnership between SFCG and concerned organizations) are to be addressed to the NGOs in order to make them more pro-active in the advocacy campaign.

## Slide 11: Lessons learned (II)
Review the role of the SFCG team in the conduct of program activities in order not to jeopardize “the ownership of the program” by all participants.
Review associations selection criteria and modalities for defining the participating group so as to ensure both program effectiveness and diligent attendance of participants.
Propose to participants a more formal recognition of their participation in training
The inland regions have a somewhat different situation insofar as relations between civil society and policymakers are rather infrequent